## StreamLine Academy Project
SlNo | Task | StartDate | EndDate | Time | Status | Resource Name
1 | Create folder structure ,created architecture and install necessary libraries | 2024-03-18 |  |  | Completed
2 | Porta Admin
3 | Models creation of AcademyRegistration,AcademyType,AppFile,EnquiryCountry,State,City,SuperAdmin & User |  |  |  | Completed
4 | Created Endpoints for above models --Endpoints Name Academy---Get,Post,Put,GetById,Delete,GetByName,GetByEmail Auth --Changepassword Enquiry--Get,Post,Put,Delete,GetById,GetByEmail |  |  |  | Completed
5 | Database table creation with index |  | 2024-03-26 |  | Completed
6 | Changes in DTO ,Quiries,Mapper,& solving conflict file as there are many changes . | 2024-03-27 | 2024-03-29 |  | Completed
7 | Authentication Module---Email Integration | 2024-04-01 | 2024-04-03 | 24hrs | Completed | Amir
8 | Login & Token response |  |  |  | Completed | Sushree
9 | Reset/Forgot password implimentation |  |  |  | Completed | Amir
10 | Change password |  |  |  | Completed | Amir
11 | authentication and authorization implimentation using JWT |  |  |  | Completed | Amir
12 | Portal Admin---Profile Management View /Update ContactInfo |  |  |  | Completed | Sushree
13 | Portal Admin---Profile Management View/Update AddressInfo | 2024-04-04 | 2024-04-05 | 16hrs | Completed | Sushree
14 | Resend reset code implimentation & test auth controller |  |  |  | Completed | Amir
15 | Upload Photo |  |  |  | Completed | Sushree
16 | Academy Admin
17 | Academy management--->(Course management) -CreateCourse GetCourseById DeleteCourse GetAllCourses UpdateCourse Modified some method | 2024-04-08 | 2024-04-10 |  | Completed | Sushree
18 | Instructor Management-CreateInstructor GetInstructorById DeleteInstructor GetAllInstructor UpdateInstructor | 2024-04-08 | 2024-04-08 |  | Completed | Amir
19 | AcademyType-CreateAcademyType GetAllAcademyType GetAcademyTypeById | 2024-04-09 | 2024-04-09 |  | Completed | Amir
20 | Course Management- CreateCourseCategory GetAllCourseCategories GetCourseCategoryById LocationManagement-CreateLocation | 2024-04-10 | 2024-04-10 |  | Completed | Amir
21 | Batch Management CreateBatch GetBatchById DeleteBatch GetAllBatches UpdateBatch | 2024-04-11 | 2024-04-11 |  | Completed | Sushree
22 | New Endpoint added in Course & modified existing endpoints | 2024-04-12 | 2024-04-12 |  | Completed | Sushree
23 | Schedule Management-CreateSchedule GetscheduleByBatchId Deleteschedule GetAllschedule Updateschedule Batch Management -GetBatchBycourseId | 2024-04-15 | 2024-04-15 |  | Completed | Sushree
24 | LocationManagement-GetAllLocation DeleteLocation GetLocationById UpdateLocation Student Management-RegisterStudent | 2024-04-15 | 2024-04-15 |  | Completed | Amir
26 | Course Content | 2024-04-16 | 2024-04-16 |  | Completed | Sushree
27 | Student controller(create,update,delete ,view,getById) | 2024-04-16 | 2024-04-16 | 8hrs | Completed | Amir
28 | Assignned Schedule to student, Students checks his all assigned Schdules, and Update Student Response modify | 2024-04-17 | 2024-04-17 |  | Completed | Amir
29 | Create Course content,schedule content in a perticular course,View content schedule | 2024-04-18 | 2024-04-19 | 16hrs | Pending
30 | View batch with assign students,Student List of each batch | 2024-04-22 | 2024-04-22 | 8hrs | Pending
31 | Student Management---> Add ,view etc | 2024-04-24 | 2024-04-24 | 8hrs | Pending
32 | Instructor Management--->Add ,view etc | 2024-04-25 | 2024-04-25 | 8hrs | Pending
33 | Profile Management---> Add ,view etc | 2024-04-26 | 2024-04-26 | 8hrs | Pending
34 | Instructor
35 | View Course and students,Take attendance and communication,profile management etc. | 2024-04-29 | 2024-05-01 | 24hrs | Pending
36 | Student
37 | View attendance and course resources,Profile management,check schedules ect | 2024-05-02 | 2024-05-06 | 24hrs | Pending
38
39 | The above task is also contain Database Creation.
40 | FrontEnd Development
41 | Setup project & folder structure,git repository | 2024-05-08 | 2024-05-08 | 8hrs | Pending
42 | Integrate Home page into angular app | 2024-05-09 | 2024-05-09 | 8hrs | Pending
43 | Create Login ,enquiry,Registaration form,change password,table,card ----->By Jahangir | 2024-05-10 |  |  | Pending
44 | Post enquiry,login,redirect,each user to the respective dashbord | 2024-05-13 | 2024-05-13 | 8hrs | Pending
45 | Portal Admin Dashboard
46 | Setup Dashboard along with links,Display enquiry list | 2024-05-14 | 2024-05-14 | 8hrs | Pending
47 | Perform crud operations on enquiry table along creation of enquiry service | 2024-05-15 | 2024-05-15 | 8hrs | Pending
48 | Register New Academy,display registered academy list along with necessary services | 2024-05-16 | 2024-05-16 | 8hrs | Pending
49 | Impliment clintside pagination and filtering on all tables | 2024-05-17 | 2024-05-17 | 4hrs
50 | implement profile management e,g logout,changepassword,upload photo etc | 2024-05-20 | 2024-05-20 | 8hrs | Pending
51 | Academy Admin Dashboard
52 | Setup Dashboard along with links. | 2024-05-21 | 2024-05-21 | 3hrs | Pending
53 | implement profile management e,g logout,changepassword,upload photo,adress etc | 2024-05-21 | 2024-05-22 | 13hrs | Pending
54 | Impliment course list,pagination anf filteration with edit ,add,update and delete for Course & validation | 2024-05-23 | 2024-05-23 | 8hrs | Pending
55 | Impliment batch pagination anf filteration with add, edit ,update and delete for batch & validation | 2024-05-24 | 2024-05-24 | 8hrs | Pending
56 | Impliment batch scheduling with student assignments to batch etc | 2024-05-27 | 2024-05-28 | 16hrs | Pending
57 | Display content and necessary operations | 2024-05-29 | 2024-05-29 | 6hrs | Pending
58 | Impliment location,student and instructor management & validation | 2024-05-30 | 2024-05-31 | 16hrs | Pending
59 | Instructor
60 | Setup Dashboard along with links & display course and student list with filtaration & pegination | 2024-06-03 | 2024-06-03 | 8hrs | Pending
61 | Take attendance & impliment communication process etc | 2024-06-04 | 2024-06-04 | 8hrs | Pending
62 | Student
63 | Setup Dashboard along with links & impliment todays schedule with calender | 2024-06-05 | 2024-06-05 | 8hrs | Pending
64 | Impliment view my batch & schedule associated with it etc & validation | 2024-06-06 | 2024-06-07 | 16hrs | Pending
65 | Impliment attendance & course materials & validation | 2024-06-10 | 2024-06-10 | 8hrs | Pending
Project End on dt -10/06/24